## Issue Log
Data Quality Issue Log — Investments BI Project
Base: investments.db (SQLite) ¦ Layer: RAW / staging ¦ Registro de problemas de qualidade de dados (findings)
Issue ID | Table | Column | Issue Type | Detection Query | Rows Affected | Distinct Values (found / expected) | Severity | Business Impact | Planned Fix | Status
1 | dim_client | client_type | inconsistent case and spaces | SELECT COUNT(DISTINCT client_type) as client_type from dim_client dc SELECT COUNT(client_type), client_type FROM dim_client GROUP BY client_type |  | 8/2 | Medium |  |  | Open
2 | dim_client | client_name | extra spaces | SELECT client_name FROM dim_client dc SELECT client_id, dc.client_name, LENGTH(dc.client_name ) as length, LENGTH(TRIM(client_name)) as clean_length FROM dim_client dc WHERE length <> clean_length | 7 |  | Low |  |  | Open
3 | dim_client | document | empty colunns | SELECT * FROM dim_client dc WHERE document is null OR TRIM(document) = '' | 2 |  | Low |  |  | Open
4 | dim_client | document | same document | SELECT dc.client_name, dc.document, count(*) FROM dim_client dc WHERE document is not null AND TRIM(document) <> '' GROUP BY dc.document HAVING COUNT(*) > 1 | 2 |  | High |  |  | Open
5 | dim_client | state | empty rows / names by acronyms and integers | SELECT dc.state , COUNT(*) FROM dim_client dc GROUP BY dc.state SELECT state, COUNT(*) FROM dim_client dc WHERE dc.state IS NULL OR TRIM(state) = '' | 5 |  | information/observation |  |  | Open
6 | dim_client | email | empty rows | SELECT dc.email FROM dim_client dc WHERE dc.email NOT LIKE '%@%' OR dc.email IS NULL OR TRIM(dc.email ) = "" | 2 |  | information/observation |  |  | Open
7 | dim_client | risk_profile | inconsistent case and spaces | SELECT dc.risk_profile , COUNT(*) FROM dim_client dc GROUP BY dc.risk_profile SELECT dc.risk_profile , COUNT(*) FROM dim_client dc WHERE dc.risk_profile IS NULL OR TRIM(dc.risk_profile ) = '' GROUP BY dc.risk_profile | 4 |  | Medium |  |  | Open
8 | dim_client | onboarding_date | out of format email | SELECT COUNT(*) FROM dim_client dc WHERE DATE(dc.onboarding_date ) IS NULL | 20 |  | High |  |  | Open
9 | dim_account | client_id | orphan FK | SELECT da.client_id, dc.client_id FROM dim_account da LEFT JOIN dim_client dc ON da.client_id = dc.client_id WHERE dc.client_id IS NULL | 1 |  | High |  | investigate the correct client and relink, otherwise isolate or remove the orphan | Open
10 | dim_account | advisor_id | orphan FK | SELECT dacc.advisor_id FROM dim_account dacc LEFT JOIN dim_advisor daa ON daa.advisor_id = dacc.advisor_id WHERE daa.advisor_id IS NULL | 1 |  | High |  | relink to a valid advisor, or isolate/remove the orphan account

## Legend
Legend / Legenda
Severity (Severidade)
High | Quebra KPI, valores financeiros errados, ou perda de registros.
Medium | Distorce agregacoes/relatorios, mas corrigivel sem perda.
Low | Cosmetico ou baixo impacto no resultado final.
Status
Open | Problema identificado, ainda nao corrigido.
In Progress | Correcao em desenvolvimento.
Fixed | Corrigido na camada limpa e validado.
Issue Types (tipos de erro esperados nesta base)
Nulls | Valores vazios / nulos.
Duplicates | Linhas ou chaves repetidas.
Inconsistent case & spaces | Mesmo valor escrito de formas diferentes.
Date formats | Datas em formatos mistos.
Orphan FK | Chave estrangeira sem correspondente na dimensao.
Negative values | Numeros negativos indevidos.
Text in numeric | Texto ('N/A','-') em coluna que deveria ser numerica.